LSAMS

Lazada Seller Activation Management System

VOLUME 6

Project Plan, Budget, Resource Loading & Implementation Roadmap

Document Type: Enterprise Implementation Roadmap

Version: 1.0

Altria Management Corporation

Confidential — For Internal Use Only

# 1. Executive Summary

This document defines the complete Project Plan, Budget Estimates, Resource Loading, and Implementation Roadmap for the Lazada Seller Activation Management System (LSAMS). It is intended to guide investors, Lazada executives, implementation partners, and PMO teams through the full delivery lifecycle.

This document covers:

- Project phases and timeline

- Resource requirements and team structure

- Development and infrastructure budget

- Deployment milestones and go-live roadmap

- Risk management and mitigation strategies

- Go-live success criteria

# 2. Project Scope

LSAMS will be delivered across three progressive phases, each building on the capabilities of the previous.

## Phase 1 — Minimum Viable Product (MVP)

The MVP phase delivers the core operational platform required for immediate business activation:

- Authentication & User Management

- Lead Import (Excel / API)

- Gabay (Field Agent) Management

- Lead Assignment Engine

- Visit Tracking with GPS Check-In

- Negotiation Tracking

- Registration Workflow with Document Management

- KPI Reporting & Executive Dashboard

## Phase 2 — Intelligent Operations

- AI-Powered Lead Assignment Engine

- Route Optimization for Field Agents

- Mobile Offline Synchronization

- Territory Heat Maps & Geo-Analytics

## Phase 3 — Enterprise Integration

- Lazada API Direct Integration

- OCR Document Verification

- AI Seller Conversion Prediction

- Business Intelligence (BI) Platform Integration

# 3. Project Timeline

Total project duration: 26 Weeks (approximately 6 months)

| Phase | Duration | Status | Key Deliverables |
| --- | --- | --- | --- |
| Discovery & Design | 4 Weeks | Completed | BRD, FDS, Architecture, Wireframes, ERD, API Design |
| Development | 16 Weeks | In Progress | Backend, Frontend, Mobile App, Integrations |
| QA & UAT | 4 Weeks | Upcoming | Functional, Performance, Security & UAT |
| Deployment | 2 Weeks | Upcoming | Infrastructure Setup, Production Deployment |
| Hypercare | 4 Weeks | Upcoming | Post Go-Live Support, Issue Resolution, KPI Validation |

# 4. Resource Loading Plan

Total team size: 15–18 resources across all disciplines.

| Department | Role | Qty | Phase Involvement |
| --- | --- | --- | --- |
| Project Management | Project Manager | 1 | All Phases |
|  | Scrum Master | 1 | Development — UAT |
| Architecture | Solution Architect | 1 | Design — Development |
|  | Database Architect | 1 | Design — Development |
| Development | Backend Lead Developer | 1 | Development |
|  | Backend Developers | 2 | Development |
|  | Frontend Developers | 2 | Development |
|  | Flutter Mobile Developer | 1 | Development — UAT |
|  | DevOps Engineer | 1 | Development — Deployment |
| Quality Assurance | QA Lead | 1 | QA — UAT |
|  | QA Engineers | 2 | QA — UAT |
| Operations | Business Analyst | 1 | Design — UAT |
|  | Trainer | 1 | UAT — Go-Live |

# 5. Estimated Development Budget

Budget estimates are based on offshore team rates in the Philippines. All figures are in US Dollars (USD).

## 5.1 Offshore Development Cost (Philippines)

| Resource Category | Estimated Cost (USD) | Notes |
| --- | --- | --- |
| Development Team (Backend, Frontend, Mobile) | $40,000 | 16-week engagement |
| QA & Testing Team | $10,000 | 4-week engagement |
| Project Management | $12,000 | Full project duration |
| Architecture & Design | $8,000 | Design phase |
| DevOps Engineering | $5,000 | Infrastructure & CI/CD |
| TOTAL DEVELOPMENT COST | $75,000 | Offshore Philippines Rates |

## 5.2 Commercial Selling Price

| Package | Recommended Price (USD) |
| --- | --- |
| Standard Package (Source Code Excluded) | $120,000 |
| Enterprise Package (Full Source Code Ownership) | $180,000 |
| AI Modules Add-On | +$20,000 – $30,000 |
| Mobile Application Add-On | +$15,000 – $25,000 |

## 5.3 Infrastructure Budget

| Environment Tier | Monthly Cost (USD) | Components |
| --- | --- | --- |
| MVP / Pilot | $300 – $500/month | 2 App Servers, 1 DB, 1 Backup, Monitoring |
| Enterprise / Production | $1,000 – $2,500/month | HA Cluster, DB Replication, CDN, Full Monitoring |

# 6. Project Milestones

| # | Milestone | Deliverable | Target Week |
| --- | --- | --- | --- |
| M1 | Architecture Approval | System Architecture Document, Database ERD, API Design | Week 4 |
| M2 | Database Completion | All Tables, Relationships, Indexes, Stored Procedures | Week 8 |
| M3 | Backend Completion | All APIs Functional, Unit Tested, Documented | Week 14 |
| M4 | Frontend Completion | All Web Screens Complete, Responsive, Validated | Week 18 |
| M5 | Mobile App Completion | iOS & Android Apps Ready, GPS Validated, Offline Sync Tested | Week 20 |
| M6 | UAT Sign-Off | User Acceptance Testing Complete, Defects Resolved, Business Approval | Week 24 |
| M7 | Production Go-Live | Production Deployed, Monitoring Active, Backups Running | Week 26 |
| M8 | Hypercare Completion | 30-Day Support Window Complete, System Stable, KPIs Validated | Week 30 |

# 7. Go-Live Rollout Roadmap

LSAMS will be deployed progressively to minimize operational risk and allow validation at each stage before expanding.

| Phase | Scope | Gabay Count | Lead Volume | Duration |
| --- | --- | --- | --- | --- |
| Pilot | Controlled Pilot Territory | 10 | 500 Leads | Week 1 |
| Expanded Pilot | Multiple Territories | 25 | 5,000 Leads | Week 2 |
| Regional Rollout | Full Regional Coverage | 50 | 20,000 Leads | Week 3 |
| National Rollout | All Territories Activated | All | Full Production Volume | Week 4 |

# 8. Risk Management

| Risk | Probability | Impact | Description | Mitigation Strategy |
| --- | --- | --- | --- | --- |
| Poor Lead Data Quality | High | High | Incomplete or inaccurate lead records from Lazada | Data cleansing module, validation rules at import, rejection reporting |
| GPS Accuracy Issues | Medium | Medium | GPS coordinate drift or indoor signal loss | GPS validation layer, manual check-in fallback, distance threshold configuration |
| Scope Expansion | Medium | High | Uncontrolled feature additions during development | Formal Change Control Board, signed change requests required |
| Delayed UAT | Medium | High | Business stakeholders unavailable for testing | Pre-schedule UAT sessions, define UAT acceptance criteria in advance |
| User Resistance | Low | High | Field agents resistant to adopting digital workflow | Early training program, pilot champions program, management endorsement |

# 9. Project Success Criteria

The LSAMS project will be considered successfully delivered when all of the following criteria are met:

|  | Criteria | Target |
| --- | --- | --- |
| 1 | UAT Pass Rate | 95% or higher across all test cases |
| 2 | System Availability | 99.5% uptime in production |
| 3 | Lead Traceability | 100% of leads have complete activity history |
| 4 | User Adoption | 90% of Gabay actively using the system within 30 days |
| 5 | KPI Reporting Accuracy | Greater than 99% accuracy on all dashboard metrics |
| 6 | Security Compliance | Zero critical vulnerabilities, OWASP Top 10 validated |

# 10. Document Sign-Off

| Role | Name | Signature / Date |
| --- | --- | --- |
| Project Sponsor |  |  |
| Solution Architect |  |  |
| Project Manager |  |  |
| Lazada Representative |  |  |